PROJECT PLAN & PROPOSAL

Waste Segregation and Plastic Reduction

SDG 12 – Responsible Consumption and Production

SDG 14 – Life Below Water

1. Project Title

Eco Sort : One Bin, Five Solutions, A Cleaner Future

2. Project Duration

12 Weeks

The project will be implemented as a school-based, student-led environmental initiative focusing on waste segregation, reduction of single-use plastics, awareness, recycling, and community participation.

3. Project Goal

The goal of this project is to promote responsible waste management among students and the school community by encouraging proper waste segregation, reducing single-use plastics, and developing sustainable consumption practices.

The project will establish waste segregation practices, conduct awareness activities, encourage plastic reduction, and measure changes in waste and plastic usage.

4. Sustainable Development Goals

SDG 12 – Responsible Consumption and Production

The project encourages students to reduce waste, reuse materials, recycle wherever possible, and make more responsible consumption choices.

SDG 14 – Life Below Water

The project connects plastic reduction with protection of oceans and aquatic ecosystems by creating awareness about the environmental impact of plastic pollution.

5. Problem Statement

Improper waste segregation and excessive use of single-use plastics can increase environmental pollution. Students may also lack awareness about which waste should be placed in different categories.

Plastic waste can eventually reach water bodies and negatively affect aquatic and marine ecosystems.

Therefore, the project proposes a student-led system that combines:

Waste Audit → Awareness → Segregation → Plastic Reduction → Recycling → Community Action → Impact Measurement

6. Objectives

- To create awareness about SDG 12 and SDG 14.

- To identify the types and quantities of waste generated in school.

- To understand existing waste disposal and plastic-use habits.

- To establish a three-category waste segregation system.

- To reduce unnecessary single-use plastic consumption.

- To encourage reusable and sustainable alternatives.

- To involve students in environmental awareness activities.

- To promote creative reuse and recycling of waste materials.

- To involve parents and the local community.

- To measure the impact of the project.

- To prepare a long-term sustainability plan for the school.

7. Target Areas

The project will focus on:

- Classrooms

- Corridors and common areas

- School campus

- Canteen/food areas

- Areas where waste is frequently generated

- Students' daily plastic-use habits

- Community surrounding the school

8. 12-WEEK ACTION PLAN

| Week | Main Activity | Major Action | Expected Output |
| --- | --- | --- | --- |
| 1 | Project Launch | Introduce SDG 12 & SDG 14, define goals, form teams | Project proposal & teams |
| 2 | Waste Audit | Identify types and quantities of school waste; conduct survey | Waste audit & survey data |
| 3 | Awareness & Research | Research plastic pollution and prepare educational materials | Posters, presentations & information material |
| 4 | Segregation Planning | Design three-bin system and decide placement/labels | Segregation system plan |
| 5 | Awareness Campaign | Assemblies, classroom talks and poster displays | School awareness campaign |
| 6 | Implementation | Install bins and begin daily segregation | Working segregation system & monitoring records |
| 7 | Plastic Reduction Drive | Conduct “No Single-Use Plastic Week” | Plastic reduction campaign |
| 8 | Community Engagement | Expert/NGO session and interactive activities | Expert session & student questions |
| 9 | Creative Recycling | Upcycling workshop using waste materials | Eco-bricks/art/planters & photos |
| 10 | Community Awareness | Awareness drive and leaflet distribution | Community awareness report |
| 11 | Evaluation | Compare initial and current data | Impact analysis & feedback |
| 12 | Final Presentation | Present results and prepare sustainability plan | Final report & sustainability recommendations |

9. Proposed Waste Segregation System

A three-bin system will be planned:

🟢 Bin 1 – Biodegradable Waste

Examples:

- Food waste

- Fruit and vegetable peels

- Other suitable organic waste

🔵 Bin 2 – Recyclable Waste

Examples:

- Paper

- Cardboard

- Suitable recyclable plastic

⚫ Bin 3 – Non-Recyclable Waste

Examples:

- Waste that cannot be practically recycled through the school's system

The bins will be clearly labelled and placed at selected locations around the school. Student monitoring teams will record segregation practices.

10. Student Team Structure

Team 1 – Research Team

Researches plastic pollution, waste management, SDG 12 and SDG 14.

Team 2 – Waste Audit Team

Records the types and quantities of waste generated.

Team 3 – Design & Innovation Team

Develops the waste segregation system and creative recycling ideas.

Team 4 – Awareness Team

Creates posters, presentations, slogans and leaflets.

Team 5 – Implementation & Monitoring Team

Monitors correct waste segregation and maintains records.

Team 6 – Community Outreach Team

Conducts awareness activities for parents and the local community.

11. Data Collection and Measurement

The project will use measurable indicators to evaluate its impact.

Before Implementation

Record:

- Types of waste generated

- Approximate quantity of waste

- Plastic usage

- Existing waste disposal practices

- Student/staff awareness

During Implementation

Record:

- Number of correctly segregated waste items/bins

- Participation in awareness activities

- Plastic reduction activities

- Use of reusable alternatives

- Monitoring observations

After Implementation

Compare:

Initial Data vs Final Data

The project will specifically compare the initial waste audit with later segregation results and analyse changes in plastic usage and feedback from students and teachers.

12. Awareness Activities

The project will include:

- School assembly presentations

- Classroom awareness talks

- Poster-making

- Display boards

- Slogans

- Informational leaflets

- Plastic pollution presentations

- Waste segregation demonstrations

- Community awareness activities

13. Plastic Reduction Initiative

A “No Single-Use Plastic Week” will be conducted.

Students will be encouraged to use:

- Reusable water bottles

- Reusable lunch boxes

- Cloth bags

- Sustainable alternatives

The initiative will focus on changing everyday habits rather than only creating awareness.

14. Creative Recycling Activity

Students will participate in a recycling/upcycling workshop.

Possible outputs include:

- Eco-bricks

- Art projects

- Planters

- Useful items made from waste materials

The purpose will be to demonstrate that some waste materials can be creatively reused instead of immediately becoming waste.

15. Community Engagement

Students will extend the project beyond the school.

Activities may include:

- Environmental expert/NGO interaction

- Student Q&A session

- Parent awareness

- Community/neighbourhood awareness drive

- Leaflet distribution

- Demonstration of correct waste segregation

The source plan specifically includes expert/NGO engagement in Week 8 and a community awareness initiative in Week 10.

16. Expected Outcomes

At the end of 12 weeks, the project is expected to produce:

- A functioning waste segregation plan.

- Increased student awareness about responsible consumption.

- Greater understanding of plastic pollution.

- Student participation in waste management.

- A documented plastic reduction campaign.

- Creative recycling/upcycling outputs.

- Community awareness activities.

- Waste audit and survey data.

- Monitoring records.

- A final impact assessment.

- A long-term sustainability plan.

17. Key Deliverables

The final project will include:

- Waste audit report

- Survey analysis

- Awareness posters and presentations

- Waste segregation system plan

- Monitoring records

- Plastic reduction campaign documentation

- Recycling workshop outputs and photographs

- Community awareness report

- Final project report

- Sustainability recommendations

18. Success Indicators

The project will measure success through:

| Indicator | Measurement |
| --- | --- |
| Waste segregation | Initial vs final segregation data |
| Plastic usage | Initial vs final plastic-use data |
| Awareness | Student/staff survey |
| Participation | Number of participating students |
| Campaign reach | Number of awareness activities conducted |
| Recycling | Number/type of upcycled products created |
| Community engagement | Number of community activities conducted |
| Sustainability | Final continuation plan |

19. Sustainability Plan

After completion of the 12-week project, the school can continue:

- Regular waste segregation

- Periodic waste audits

- Plastic reduction campaigns

- Student environmental monitoring teams

- Awareness activities

- Recycling/upcycling activities

- Annual review of waste management practices

The final week will include recommendations for continuing these practices into the following academic year.

20. Final Project Flow

IDENTIFY → RESEARCH → PLAN → CREATE AWARENESS → IMPLEMENT → REDUCE → RECYCLE → ENGAGE COMMUNITY → MEASURE → SUSTAIN

This makes the project a continuous action cycle rather than a one-time awareness activity.

21. Conclusion

The Waste Segregation and Plastic Reduction project provides a structured 12-week approach to improving waste management within the school community.

The project begins by understanding the existing waste problem, followed by research and awareness. It then moves into the practical implementation of waste segregation and plastic reduction, followed by recycling, community participation, evaluation, and long-term sustainability.

Through student participation and measurable activities, the project aims to develop responsible waste-management habits and support the objectives of

SDG 12 and SDG 14.

________________________________________________________________________________