PROJECT PROPOSAL
Digital Literacy and Safe Internet
Introduction
Digital technology and the internet have become an essential part of students' education, communication and daily lives. Along with its benefits, unsafe or irresponsible internet use can expose students to risks such as cyberbullying, privacy concerns, misinformation, unsafe browsing and misuse of personal information.
This project aims to develop students' digital literacy, cyber safety awareness, critical thinking and responsible online behaviour. Through surveys, research, awareness campaigns, workshops, practical activities, peer education and community outreach, students will learn to become safe, ethical and responsible digital citizens. The project is aligned with SDG 4 – Quality Education and SDG 9 – Industry, Innovation & Infrastructure.

12-Week Project Plan
Week 1 – Project Launch
Introduce digital literacy, safe internet practices and responsible digital citizenship. Identify target groups and expected outcomes. Form student committees for Awareness, Research, Cyber Safety and Documentation and collect students' initial ideas.
Week 2 – Needs Assessment
Conduct a baseline survey to understand students' digital usage, online habits, cyber-safety awareness and common online risks. Identify areas where students need greater awareness.
Week 3 – Research & Planning
Students research important topics such as cyberbullying, privacy, digital footprint, misinformation and safe browsing. Based on their findings, plan awareness activities and workshop themes.
Week 4 – Campaign Design
Students prepare awareness materials such as posters, presentations, videos, slogans and safe-internet guidelines to communicate key cyber-safety messages effectively.
Week 5 – Awareness Drive – Phase 1
Conduct classroom sessions and school assemblies focusing on digital citizenship, cyber ethics and responsible social media use.
Week 6 – Cyber Safety Workshop
Conduct an expert/trained-educator session on online threats, password safety, phishing and data privacy. Students learn practical ways to protect themselves online.
Week 7 – Practical Digital Skills
Conduct hands-on activities on email etiquette, safe online research, identifying fake news and using educational digital tools safely.
Week 8 – Peer Education & Campaign
Students take the lead by conducting peer-awareness sessions, skits and digital campaigns to spread safe-internet messages among other students.
Week 9 – Responsible Usage & Innovation
Students create positive digital content such as blogs, posters and short videos promoting responsible internet use and positive online engagement.
Week 10 – Community Outreach
Conduct an awareness session for parents on children's digital use, cyber safety, responsible screen habits and ways to support safe internet use at home.
Week 11 – Evaluation & Impact Measurement
Conduct the post-survey and compare the results with the baseline survey. Evaluate changes in students' awareness, understanding and digital practices.
Week 12 – Presentation & Sustainability
Students present the project outcomes, student-created work and recommendations to school leadership. Prepare the final report, cyber-safety resources and a sustainability plan for continuing digital-safety awareness in school.




Expected Outcomes
By the end of the project, students will:
· Demonstrate improved digital literacy.
· Understand basic cyber-safety practices.
· Recognise common online risks.
· Practise responsible digital citizenship.
· Develop critical thinking while using online information.
· Understand the importance of privacy and data protection.
· Promote safe and ethical digital behaviour among peers.
· Create useful digital-safety awareness resources.
Key Project Deliverables
· Baseline & post-survey reports 
· Awareness materials 
· Workshop reports 
· Student-created digital content 
· Cyber-safety guidelines 
· Peer education records
· Parent outreach report 
· Student portfolios
·  Final impact report                                                                                                                                         
